## Sheet1
ITSC-3155 Software Engineering
Sprint Backlog
Story Tasks | Story Point | Assigned to | Estimated Effort | Day1 | DAY 2 | DAY 3 | DAY 4 | DAY 5 | DAY 6 | Status | SPRINT REVIEW
User Story #1 | 8 | Preston | 26.5 | 7.5 | 6 | 11 | 1 | 1 | 0 | Done
Design and implement database schema for menu items | 5 | Preston | 5 | 2 | 1 | 1 | 1 | 0 | 0 | Done | 1
Develop backend API endpoint to create new menu items | 1 | Preston | 8 | 3 | 2 | 2 | 0 | 1 | 0 | Done | 1
Build and validate frontend form for creating menu items | 1 | Preston | 6 | 1 | 2 | 3 | 0 | 0 | 0 | Done | 1
Develop testing | 1 | Preston | 7.5 | 1.5 | 1 | 5 | 0 | 0 | 0 | Done | 1
User Story #2 | 5 | Walker | 15 | 4 | 3 | 3 | 3 | 2 | 0 | Done
Extend inventory data model to support threshold alerts | 3 | Walker | 5 | 2 | 1 | 1 | 1 | 0 | 0 | Done | 1
Implement backend logic to check inventory levels on order creation | 1 | Walker | 7 | 2 | 2 | 2 | 1 | 0 | 0 | Done | 1
Develop testing | 1 | Walker | 3 | 0 | 0 | 0 | 1 | 1 | 1 | Done | 1
User Story #3 | 5 | Jason | 15 | 5 | 4 | 3 | 2 | 1 | 0 | Done
Design database query for fetching all orders | 2 | Jason | 5 | 2 | 1 | 1 | 1 | 0 | 0 | Done | 1
Implement API endpoint for listing orders | 1 | Jason | 4 | 1 | 2 | 1 | 0 | 0 | 0 | Done | 1
Implement API endpoint for order detail retrieval | 1 | Jason | 4 | 1 | 1 | 2 | 0 | 0 | 0 | Done | 1
Develop testing | 1 | Jason | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 1
User Story #4 | 8 | Tevin | 20 | 6 | 6 | 5 | 3 | 0 | 0 | Done
Design data model for tracking dish popularity | 3 | Tevin | 5 | 2 | 2 | 1 | 0 | 0 | 0 | Done | 2
Implement backend logic to calculate popularity metrics | 2 | Tevin | 7 | 2 | 2 | 2 | 1 | 0 | 0 | Done | 2
Create API endpoint for popularity report retrieval | 1 | Tevin | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 2
Develop testing | 2 | Tevin | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 2
User Story #5 | 8 | Jason | 20 | 6 | 5 | 4 | 3 | 2 | 0 | Done
Design feedback data model and schema | 4 | Jason | 5 | 2 | 1 | 1 | 1 | 0 | 0 | Done | 2
Implement backend logic to ingest and store customer feedback | 2 | Jason | 6 | 2 | 2 | 1 | 1 | 0 | 0 | Done | 2
Create API endpoint for retrieving feedback summaries | 1 | Jason | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 2
Develop testing | 1 | Jason | 3 | 1 | 1 | 0 | 0 | 1 | 0 | Done | 2
User Story #6 | 5 | Nicholas | 12.5 | 3 | 3 | 2.5 | 2 | 1 | 1 | Done
Design promo code data model and schema | 2 | Nicholas | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 2
Implement backend logic for promo code creation and validation | 1 | Nicholas | 5 | 1 | 1 | 1 | 1 | 1 | 0 | Done | 2
Create API endpoint for managing promo codes | 1 | Nicholas | 2.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | Done | 2
Develop testing | 1 | Nicholas | 1 | 1 | 0 | 0 | 0 | 0 | 0 | Done | 2
User Story #7 | 5 | Nicholas | 12 | 2 | 3 | 2 | 2 | 2 | 1 | Done
Design revenue data model and schema | 2 | Nicholas | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 1
Implement backend logic for daily revenue calculation | 1 | Nicholas | 3 | 1 | 1 | 0 | 1 | 0 | 0 | Done | 1
Create API endpoint for daily revenue report | 1 | Nicholas | 3 | 0 | 1 | 1 | 0 | 1 | 0 | Done | 1
Develop testing | 1 | Nicholas | 2 | 0 | 0 | 0 | 0 | 1 | 1 | Done | 1
User Story #8 | 3 | Preston | 9 | 2 | 2 | 1.5 | 1.5 | 1 | 1 | Done
Design data model for date-range order lookup | 1 | Preston | 2.5 | 1 | 1 | 0.5 | 0 | 0 | 0 | Done | 1
Implement API endpoint for retrieving orders by date range | 1 | Preston | 3 | 0 | 1 | 1 | 1 | 0 | 0 | Done | 1
Implement backend filtering and validation logic | 0.5 | Preston | 2.5 | 0 | 0 | 1 | 1 | 0.5 | 0 | Done | 1
Develop testing | 0.5 | Preston | 1 | 0 | 0 | 0 | 0 | 0.5 | 0.5 | Done | 1
User Story #9 | 8 | Walker | 24 | 6 | 5 | 4 | 4 | 3 | 2 | Done
Design data model for guest checkout | 4 | Walker | 6 | 2 | 2 | 1 | 1 | 0 | 0 | Done | 1
Implement API endpoint for guest checkout | 2 | Walker | 8 | 2 | 2 | 2 | 1 | 1 | 0 | Done | 1
Implement business logic to bypass authentication for guest orders | 1 | Walker | 6 | 1 | 1 | 1 | 1 | 1 | 1 | Done | 1
Develop testing | 1 | Walker | 4 | 1 | 0 | 0 | 1 | 1 | 1 | Done | 1
User Story #10 | 5 | Nicholas | 15 | 4 | 3 | 3 | 2 | 2 | 1 | Done
Design data model for payment options | 2 | Nicholas | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 1
Implement backend logic to save and validate payment methods | 1 | Nicholas | 5 | 1 | 1 | 1 | 1 | 1 | 0 | Done | 1
Create API endpoint for listing payment options | 1 | Nicholas | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 1
Develop testing | 1 | Nicholas | 3 | 1 | 0 | 1 | 1 | 0 | 0 | Done | 1
User Story #11 | 3 | Tevin | 9 | 2 | 3 | 3 | 1 | 0 | 0 | Done
Design data model for order type selection | 2 | Tevin | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 1
Implement backend logic to process takeout/delivery selection | 1 | Tevin | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 1
Create API endpoint for setting order type during checkout | 0.5 | Tevin | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | 1
Develop testing | 0.5 | Tevin | 2 | 0 | 0 | 1 | 1 | 0 | 0 | Done | 1
User Story #12 | 5 | Walker | 15 | 4 | 3 | 3 | 2 | 2 | 1 | Done
Design data model for order tracking | 2 | Walker | 4 | 2 | 1 | 1 | 0 | 0 | 0 | Done | 1
Implement backend logic for tracking status | 1 | Walker | 5 | 1 | 1 | 1 | 1 | 1 | 0 | Done | 1
Create API endpoint for order status retrieval | 1 | Walker | 3 | 0 | 1 | 1 | 0 | 0 | 1 | Done | 1
Develop testing | 1 | Walker | 3 | 1 | 0 | 0 | 1 | 1 | 0 | Done | 1
User Story #13 | 3 | Jason | 9 | 2.5 | 2 | 2.5 | 1.5 | 0.5 | 0 | Done
Design data model for menu search filters | 1 | Jason | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 2
Implement backend search logic for filtering menu items | 1 | Jason | 2.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | 0 | Done | 2
Create API endpoint for menu search by type | 0.5 | Jason | 2 | 0.5 | 0.5 | 0.5 | 0.5 | 0 | 0 | Done | 2
Develop testing | 0.5 | Jason | 1.5 | 0 | 0 | 0.5 | 0.5 | 0.5 | 0 | Done | 2
User Story #14 | 5 | Preston | 20 | 5 | 5 | 4 | 3 | 2 | 1 | Done
Design data model for ratings and reviews | 2 | Preston | 5 | 2 | 1 | 1 | 1 | 0 | 0 | Done | 2
Implement backend logic to submit and retrieve reviews | 1 | Preston | 6 | 2 | 2 | 1 | 1 | 0 | 0 | Done | 2
Create API endpoint for fetching review summaries | 1 | Preston | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 2
Develop testing | 1 | Preston | 5 | 0 | 1 | 1 | 1 | 1 | 1 | Done | 2
User Story #15 | 3 | Nicholas | 12 | 3 | 2.5 | 2 | 2 | 1.5 | 1 | Done
Design data model for promo code application | 1 | Nicholas | 4 | 1 | 1 | 1 | 1 | 0 | 0 | Done | 1
Implement backend validation logic for applying promo codes | 1 | Nicholas | 3 | 0.5 | 1 | 0.5 | 0.5 | 0.5 | 0 | Done | 1
Create API endpoint for promo code redemption at checkout | 0.5 | Nicholas | 3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | Done | 1
Develop testing | 0.5 | Nicholas | 2 | 1 | 0.5 | 0.5 | 0 | 0 | 0 | Done | 1
User Story #16 | 3 | Tevin | 9 | 3 | 2 | 2 | 1 | 1 | 0 | Done
Design data model for customer loyalty calculation | 1 | Tevin | 2 | 1 | 1 | 0 | 0 | 0 | 0 | Done | 2
Implement backend logic for loyalty scoring | 1 | Tevin | 3 | 1 | 1 | 1 | 0 | 0 | 0 | Done | 2
Create API endpoint for loyalty insights retrieval | 0.5 | Tevin | 2 | 0 | 1 | 1 | 0 | 0 | 0 | Done | 2
Develop testing | 0.5 | Tevin | 2 | 0 | 0 | 0 | 1 | 1 | 0 | Done | 2
TOTAL |  |  | 243 | 65 | 57.5 | 55.5 | 34 | 22 | 9